## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | BY, 3/9 | Pass | BY, 3/29
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | BY, 3/9 | Pass | BY, 3/29
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | AI, 3/9 | Pass | BY, 3/29
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | BY, 3/9 | Pass | BY, 3/29
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | AI, 3/9 | Pass | BY, 3/29
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | AI, 3/9 | Pass | BY, 3/29
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | BY, 3/9 | Pass | BY, 3/29
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | JC, 3/10 | Pass | BY, 3/29
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | JC, 3/10 | Pass | BY, 3/29
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | JC, 3/10 | Pass | BY, 3/29
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | JC, 3/10 | Pass | BY, 3/29
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | JC, 3/10 | Pass | BY, 3/29
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | JC, 3/10 | Pass | BY, 3/29
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | JC, 3/10 | Pass | BY, 3/29
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | JC, 3/10 | Pass | BY, 3/29
As a player I want to make a simple move diagonally so that I can move my pieces forward in the game. | Given that there is no jump move available and there is an empty space one of my pieces can jump to, when I move my piece diagonally to that square, then I should be able to submit that jump as a move |  |  | Pass | JC, 3/29
| Given that there is a piece in the square I want to move to, when I try to move to that space, then I should not be able to make that move |  |  | Pass | JC, 3/29
| Given that a jump move is available to be played, when it's my turn and I try to make a simple move, then I should not be able to make the move. |  |  | Pass | JC, 3/29
| Given that I already made a move, when I try to make another move before submitting, then I should not be able to make the other move |  |  | Pass | JC, 3/29
As a player, I want to log out of a game so that I can't be challenged to a game while I'm away. | Given that I'm a player that wants to sign out, when I see the home page then I have a means of signing out |  |  | Pass | AL, 3/29
| Given that I'm a player in a game, when I'm in a game, then I should not be able to log out without first finishing the game |  |  | Pass | AL, 3/29
| Given that I'm a player that wants to log out and I'm not in a game, when I click on the sign out link, then I should go back to the initial page |  |  | Pass | AL, 3/29
As a player, I want to make a jump move so that I can capture an opponents piece | Given that a jump move can be made when it's the player's turn to play then the jump move must be made for the game to progress. |  |  | Pass | BY, 3/29
| Given that more than a single jump move can be made, when the player moves, then the player should be able to choose one out of all the jump moves to play |  |  | Pass | BY, 3/29
| Given that a piece is in front of another piece of different colors, when the jump move is played, then the piece that is jumped over is removed from the game. |  |  | Pass | BY, 3/29
| Given that there is a piece in front of another piece of a different color, when there is another piece occupying the square where the jumping piece would land on, then the jump move can’t be made. |  |  | Pass | BY, 3/29
| Given that there is a piece I can jump over, when I try to jump over more than a single piece, then I should not be able to make that jump move |  |  | Pass | BY, 3/29
| Given that there is a piece I can jump over, when I try to make a jump move backwards with a non king piece, then I should not be able to make that move. |  |  | Pass | BY, 3/29